This is a checklist of suggested activities to support the implementation of a collective impact initiative, to be executed by the backbone organization and initiative partners

Collective Impact Initiative Implementation Activities

Legend: Strategic Activities:; Activities that involve strategic oversight, external communication, research and evaluation, or policy.. Logistical/Tactical Activities:; Activities that involve logistical support, internal communication, note-taking and dissemination, and scheduling.

1. Maintain Strategic Coherence of the Effort

- Accountability, Evaluation, & Guidance

- Analyze and monitor progress (including Working Group progress) against specific strategies and goals identified by Working Groups

- Continue to develop outcome indicators and performance measures to evaluate progress and to inform system improvement

- Begin to collect indicators and develop data collection processes

- Encourage sharing of best practices among the Executive Committee, Steering Committee members, and the Working Groups

- Monitor outcome indicators and performance measures related to Working Group to evaluate progress and to inform system improvement

- Knowledge Sharing, Overall Logistical Support

- Coordinate research and other activities currently underway by participants in the <Insert Initiative Name>

- Encourage sharing of best practices among the Executive Committee, Steering Committee members, and the Working Groups

- Monitor and enable easy dissemination of Common Agenda and/or Blueprint for Implementation (if developed)

- Provide overall logistical support for meetings

2. Help Coordinate through Executive Committee and Steering Committee

- Management and Facilitation

- Identify and raise issues / concerns with the Executive Committee and Steering Committee

- Assist development of agendas/ draft agendas for Executive Committee meetings, Steering Committee meetings, and other meetings as necessary

- Facilitate meeting at weekly Executive Committee meetings/calls

- Create decks and materials for Executive Committee meetings, Steering Committee meetings, and other meetings as necessary

- Maintain a high level perspective to guide and participate in Executive Committee meetings as necessary

- Follow-up and manage next steps that come out of Executive Committee meetings, Working Group meetings, and other meetings as necessary

- Manage meeting logistics (e.g., dial-in, attendance, cancellations, etc.)

- Consolidate Working Group updates for Executive Committee and Steering Committee

- Notify Steering Committee and / or Executive Committee of concerns or issues that might stall advancement

- Coordinate across Executive Committee members

- Summarize meeting notes and next steps

3. Fundraising and Outreach

- Coordination, Communication, & Policy

- Engage with and / or facilitate community engagement with a broader audience, as appropriate, to build buy-in from additional stakeholders

- Facilitate communication between the Executive Committee, Steering Committee, Co-Chairs, and Working Groups to understand challenges at the Working Group level and strategic coherence at the Executive Committee level

- Develop external communications materials and a comprehensive community engagement and communications plan

- Coordinate with other major initiatives in the community, as appropriate, to minimize redundancies and to align strategies and actions

- Note potential legislative agenda, policy, and funding recommendations with guidance of Working Groups, Steering Committee, and Executive Committee

- Respond to requests for information by community partners and allies as appropriate, in coordination with Working Groups, Steering Committee, and Executive Committee

- Develop a plan for on-going funding for <Insert Initiative Name>’s work

4. Establish and Support Working Groups

- Establish Working Groups

- Work with Steering Committee and Executive Committee to develop a list of priority Working Group members and Co-Chairs

- Invite Working Group members through letter, calls, and 1-on-1 meetings

- Orient Working Group Co-chairs and members to their roles

- Establish Working Group goals with the Steering Committee, and refine with Working Group Co-Chairs

- Project Management, Facilitation, and Support

- Guide Working groups to develop specific goals, metrics, and implementation strategies based on the Common Agenda

- Assist development of meeting agendas (i.e. provide draft agenda)

- Assist co-chairs / develop meeting materials including presentation

- Research topics relevant to strategy development

- Develop talking points for Working Group co-chairs

- Assist Working Group co-chairs with completing report back to groups

- Help Working Group co-chairs incorporate Executive Committee feedback on goals, metrics, and strategies

- Follow-up and manage next steps that come out of Working Group meetings

- Plan and schedule working group meetings

- Support the co-chairs to facilitate meetings

- Ensure attendee lists are up to date

- Manage meeting logistics (e.g., video conferencing, attendance, lunch, cancellations, send final lists to admin staff etc.)

- Print meeting materials and talking points